## Sheet1
2016 Project Budget
| Project: | Assessment Manager
| Designer: | Liam Mills
| Supervisor | Snjezana Soltic
EXPENDITURE
A: SALARY
| Design charge rate: |  | 15.25 | <---- enter $/hr
Budget
|  | Start date | Hours | Cost
1 | Initial negotiation |  | 1 | 15.25
2 | initial plan, budget & contract |  | 4 | 61
3 | Client meetings |  | 7.5 | 114.375
4 | Design of Examiner GUI |  | 7 | 106.75
5 | Design of Assessment Designer GUI |  | 12 | 183
6 | Backend programming for Examiner |  | 16 | 244
7 | Backend programming for Assessment Designer |  | 35 | 533.75
10 | Preparation of Interim Report |  | 8 | 122
11 | Preparation of Presentation |  |  | 0
12 | Preparation of Final Report |  |  | 0
13 |  |  | 90.5 | 1380.125
14
C: FINAL QUOTE & PROFIT / (LOSS) | Overhead allowance: | 50%
| Profit | 40%
Budget
| Estimated Cost before profit: | 2070.1875
| Gross Profit: | 828.075
| Quoted Price: | 2898.2625