## Sheet1
2016 Project Budget
Semester 1
| Project: | Assessment Manager
| Designer: | Liam Mills
| Supervisor | Snjezana Soltic
EXPENDITURE
SALARY
| Design charge rate: |  | 15.25 | <---- enter $/hr
|  |  | Budget |  | Actual
|  | Start date | Hours | Cost | Hours | Cost
1 | Initial negotiation |  | 1 | 15.25 | 1 | 15.25
2 | initial plan, budget & contract |  | 4 | 61 | 8 | 122
3 | Client meetings |  | 7.5 | 114.375 | 4 | 61
4 | Design of Examiner GUI |  | 13 | 198.25 | 15 | 228.75
5 | Design of Assessment Designer GUI |  | 33 | 503.25 | 16 | 244
6 | Backend programming for Examiner |  | 20 | 305 | 0 | 0
7 | Backend programming for Assessment Designer |  | 40 | 610 | 32 | 488
10 | Preparation of Interim Report |  | 20 | 305 | 10 | 152.5
11 | Preparation of Presentation |  |  | 0
12 | Preparation of Final Report |  |  | 0
13 |  |  | 138.5 | 2112.125 | 86 | 1311.5
14
FINAL QUOTE & PROFIT / (LOSS)
| Overhead allowance: | 50%
| Profit | 40%
Budget
| Estimated Cost before profit: | 3168.1875
| Gross Profit: | 1267.275
| Quoted Price: | 4435.4625