## Sheet1
Semester 1 2016
Outcomes |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14` | Week 15 | TOTALS
1 | Initial negotiation | [15 empty] | 1 | bar: Week 1
| Actual hours | [15 empty] | 1 | bar: Week 1 to Week 15
2 | initial plan, budget & contract | Week 1: 2; Week 2: 2 | 4
| Actual hours | Week 1: 2; Week 2: 2; Week 3: 4 | 8
3 | Client meetings | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 7.5
| Actual hours | Week 1: 0.5; Week 2: 0.5; Week 3: 0.5 | 1.5
4 | Design of Examiner GUI | Week 2: 3; Week 11: 10 | 13
| Actual hours | Week 2: 3 | 3
5 | Design of Assessment Designer GUI | Week 3: 3; Week 4: 10; Week 12: 10; Week 13: 10 | 33
| Actual hours | Week 3: 2; Week 4: 8; Week 5: 6 | 16
6 | Backend programming for Examiner | Week 9: 10; Week 10: 10 | 20
| Actual hours | [15 empty] | 0
7 | Backend programming for Assessment Designer | Week 5: 10; Week 6: 10; Week 7: 10; Week 8: 10 | 40
| Actual hours | Week 3: 2 | 2
10 | Preparation of Interim Report | Week 14`: 10; Week 15: 10 | 20
| Actual hours | [15 empty] | 0
11 | Preparation of Presentation | [15 empty] | 0
| Actual hours | [15 empty] | 0
12 | Preparation of Final Report | [15 empty] | 0
| Actual hours | [15 empty] | 0